## worklist
Worklist | last updated: 3.9.2004
Task | Comments | Who | Priority | Status | Type | When
Get the rigging surveyed by Brion Toss and crew | this FRI | W | MUST | D
Buy spare parts for plumbing | need hoses 3/4'' and 1 1/2'' | W | MUST |  | supply
mount LED tri-color anchor light | have the light and the bracket. Need a tap and screws. | SW | MUST | D | job
replace both anchor shackles | round hoop will need to be punched out (have all replacements) | W | MUST |  | job
spare hoses for raw water circuit | must be marine grade and wire reinforced | W | MUST |  | supply
Buy spare parts for engine | consider buying a cruise kit for the perkins ($850). At minimum need: extra belt, filters, impeller, upper and lower gasket set, lift pump (have extra), fuel washer kit. Consider -- fresh water and salt water pumps. | W | MUST | D | supply
Buy spare parts for the current alternator | new brushes | W | QUAL |  | supply
Buy spare packing material for gland | gore tex -- need to measure. http://www.e-marine-inc.com/products/gfopacking/packing.html | W | QUAL |  | supply
Replace main winch with #22 | andersen preferred ($400 at pyacht) | W | QUAL |  | job
inspect and grease all winches | have all parts | S | MUST |  | job
Buy then label all spare parts bins | have two medium bins currently | S | MUST | D | job
Change the oil in the gearbox | buy more ATF | W | QUAL |  | job
replace bobstay and remove turnbuckle | PT trip | Toss | MUST | D
replace bobstay shrouds | PT trip | Toss | MUST | D
replace boomkin shrouds | PT trip | Toss | MUST | D
add toggle to upper end of forestay | PT trip | Toss | MUST | D
replace all halyards | PT trip | TOSS | QUAL | D | job
Tef-Gel mast pin | PT trip | Toss | MUST | D
replace throughbolts and clevis pins on mast | PT trip | Toss | MUST | D
replace existing main sheet arrangement with traveler system located in front of the dodger | PT trip | Toss | MUST | D
replace lifelines | PT trip (will use Spectra line) | Toss | MUST | D
tune the standing rigging | at the dock with the gauges and then at sea. Did this once already in March. | SW | MUST | D | job
Devise reefing system with help from Brion Toss for mains'il tack | this turns out to be pretty straightforward -- we just need to add a reefing horn on the gooseneck and buy or build a cunningham to flatten the leech of the sail. | W | MUST | D | job
Test the storm sails -- trys'il and storm jib | we may not actually have a storm jib for the head stay. If this is the case we should buy one at Schautthauer or North sails before taking off | SW | MUST | D | skill
Test the reacher | as part of the rigging survey Brion found that the block for the tack line needs to be run outside the forestay. Also, need to switch the yankee halyard with the drifter (after a crane is installed on the front of the masthead) | SW | MUST | D | skill
Fix the play in the tiller | designed the part. Need to get the materials (ertalyte PET) cut in Seattle. Update: work currently in progress at clear-cut plastics in Fremont. The part is being made out of UHMW plastics instead of PET, however. If this doesn't work we can get a new tiller from Bud. | W | MUST | D
Replace zinc in heat exchanger | stewart's marine -- these are 3/4'', Roland has these as well. | W | MUST | D
Replace all zincs (exterior) | another haulout task | SW | MUST | D
Extra parts for gooseneck | also needs to be disassembled and put back together with blue loktite. Doesn't use any nuts -- only pins | W | MUST | D
change all fuel filters | do this a week or two before heading to Neah Bay -- the secondary filter requires bleeding the lines
Coat all standing rigging, turnbuckle threads etc with anhydrous lanolin | did this in March -- will need to do it again before taking off | S | MUST | D | job | 2004-08-02
clean and inspect ALL sails | take the sails to Shautthauer sails down the street -- we will clean the sails ourselves. 6.25 -- half done. | S | MUST | D | job
change raw water impeller |  | W | MUST | D
Tape shorepower outlet water tight | use plastic and tape | S | MUST |  | job
Install new shore power inlet | have the parts -- can pot the new hardware after drilling out the old ones. The existing one can be taped up water tight before leaving WA | W | QUAL |  | job
Boarding ladder | I think we're better off getting or making the rope kind at first | S | MUST | D | supply
Buy a spare handle for the windlass | get a piece of aluminum tubing | S | QUAL |  | supply
Buy a spare ignition | fisheries supply | W | QUAL |  | supply
Top off propane | before heading to neah bay -- one tank is full | W | MUST | D | supply
varnish saloon table | high-gloss finish/varnish -- have varnish | S | NICE |  | job
varnish cabin sole | satin-finish -- need to use non-skid powder in stratigic areas | W | MUST | D
Oil all interior teak woods | have lemon oil | S | MUST | D
Buy another pigtail for propane | sure marine | W | MUST | D
test propane switch | once we have another pigtail installed | W | MUST | D
Find out how to override propane solenoid if necessary | look this up | W | MUST | D | job
replace/fix float switch in small bilge pump | Bilge (aft) needs to be thoroughly cleaned. Large float switch is not mounted to anything and the cable is too short -- a splice needs to be added an mounted to bottom of bilge. Small float pump is not working and needs to be replaced. Note that pumps are connecte directly to batteries and will need to be physically disconnected before work begins. | W | QUAL |  | job
Test and replace all exterior lights as necessary | also get replacement lights for everything | SW | MUST | D | job
Clean the air filter for the engine and replace oil | need to get some solvent for this job | W | MUST | D
have sanitug steam clean the bilges | call Matt Reichl | W | MUST | D
Clean bilges |  | W | MUST | D | job
Top off fuel tanks | Neah bay | W | MUST |  | supply | 2004-08-02
Top off water tanks | final top off at PT | W | MUST |  | supply | 2004-08-02
inspect all lifelines and service | broken swag on forward stbd side needs to be replaced | W | MUST | D
varnish and epoxy bowsprit platform | use neat west system epoxy for two coat | S | MUST | D | job
Buy extra zincs | two diver's dreams; what size? | S | MUST | D | supply | 2004-10-20
Print out spare parts list for Beth Leonard's book |  | W | QUAL |  | job
paint the name on the dinghy | research best paint -- IN PROGRESS | S | MUST | D
get the dinghy outboard serviced | ballard inflatable -- this is a moot issue if we buy a new outboard motor (see below) | W | MUST | D | supply
cancel Warren's cell phone | ATT wireless | W | MUST | D
finalize plans for Ha-Ha 2004 crew | talk to IGS | SW | QUAL |  | job
clean all strainers | both are new -- there's one in the engine room and one under the head. Close seacocks before checking! | S | MUST | D | job | 2004-08-02
remove the extra halyard for the main and replace with messenger lines | the line is currently getting weathered unnecessarily | S | MUST | D
buy spare parts for rigging | need long wire and some way of swaging terminals -- also should find out how to use sta-lok terminals | W | MUST | D | supply
Cancel mailbox | may not need to do this if we keep S&S for our mail forwarding | S | MUST | D
Cancel internet service | cascadelink.com | W | MUST | D
Cancel moorage |  | S | MUST | D
Get the MOM8 overboard module re-certified | contacted their support team but it looks like the closest 'official' service center is in Alameda | S | QUAL |  | supply | 2004-09-15
Buy small scale NOAA chart of Seattle to SF | at Captain's | W | MUST | D | supply
Buy charts from Bellingham chart printers (3/4 scale) for trip through PV | can do this in SD | W | MUST | D | supply
Cash and travelers checks | before leaving for Mexico in the fall | S | QUAL |  | supply | 2004-10-20
cancel all credit cards except Amex and boat card (warren) |  | SW | MUST | D
mount diesel and water jerry jugs |  | S | MUST | D | job
mount dinghy |  | W | MUST | D | job
make snubber | this will be done as soon as my splices are better | W | MUST | D
buy enough oil for three changes | 30W | S | MUST | D | supply
sell s/v Shedonist | ??? | SW | MUST | D
sell Jetta | in April while Steph's in Spain | W | MUST | D
buy a cable and lock for the dinghy | bike shop? Combo lock | S | MUST | D | supply
replace sheered bolt on boom gallows | Tacoma screw -- also need to pickup a plastic bolt sizer tool | W | QUAL |  | job
buy a wooden dowel (1/2'' by 36'') to use with fuel tanks | limback lumber | W | MUST | D
put waypoints into GPS | transfer from laptop | W | MUST |  | job
secure laptop to chart table |  | S | MUST | D
mount liferaft on deck | ??? | W | MUST | D | job
seize all deck shackles |  | S | MUST | D | job
Service all fire extinguishers | there's a place right down the block were we can take 'em | S | MUST | D | supply
change billing address to Parry's in CA |  | S | MUST | D
emergency bilge pump handle | I think the one for the discharge pump in the head will work | S | MUST | D
replace alternator belt | a turnbuckle works best for this -- 6.21, starting to squeal upon startup so definitely time for some tightening. Also, inspect for wear and replace if necessary (Stewart's Marine in Ballard) | W | MUST | D | job
spare alternator belt | stewart's marine --40 or 41 is OK | W | MUST | D | supply
Get flexible solar panels | add at least two more in the 2 amp range -- may be possible to just plug these into cigarette 12v plug (ABS Alaskan) | W | MUST | D
Get towable generator | ABS Alaskan | W | MUST | D
tighten fasteners for steering vane | get some locktite on all the bolts | W | MUST | D | job
install or make preventer for boom | ??? | W | MUST | D | job
Replace gate valve on exhaust | replace with ball valve | SW | QUAL |  | job
First AID KIT | compile list from Leonard book; assign prescriptions to Warren | S | MUST | D | supply
Get any other prescription meds |  | S | MUST | D
Get the diesel survey | call mark | W | MUST | D
talk to Jill about EPIRB |  | S | MUST | D | supply
replace the light in the main compass | fix or install new bulkhead compass ($229 at west marine) | S | MUST | D | supply
rewire all mast electronics |  | SW | QUAL | D
mount RADAR reflector |  | SW | MUST |  | job
tools from snap-on | need feeler guages and a 3/8'' torque wrench and set of taps | W | QUAL |  | supply
buy and rig jack lines (test with harnesses) |  | S | MUST | D | supply
paint mast |  | S | QUAL | D | job
cancel everclean service |  | W | MUST | D | job
replace coax connecion at top of mast |  | W | MUST | D | job
clean, sanitize water tanks |  | S | MUST | D
install new antenna for VHF at top of mast |  | W | MUST | D | job
put together spare bolts/fastener's box | Tacoma screw | W | MUST | D | supply
Create a list of MUSTs based on the survey that Brion Toss completed for the boat in Feb | Brion should be sending along his complete list by the middle of March | W | MUST | D
grease seacocks | remember to do this in the yard during the maxprop install | S | QUAL |  | job
Repack stuffing box | need GFO goretext packing material. Need to measure proper size (diameter of packing threads minus shaft divded by two). | W | QUAL |  | job
inspect cutlass bearing | at haulout -- we also have a spare on hand | E | QUAL
add mast butt landing | PT trip | W | QUAL
Get rid of mast steps, fill holes, add new folding mast steps at top of mast | someday | W | QUAL | D
replace tangs with larger, bushed ones | PT trip | W | QUAL | D
remove lifter stays | PT trip | W | QUAL | D
replace spreader tips with seizings | someday | W | QUAL | D
replace halyards (main, staysi'l, yankee) with sta-set-x -- keep the new yachtbraid one for use with the drifter | PT trip | W | QUAL | D
add 2:1 purchase to the outhaul | someday | W | QUAL
re-engineer the reef-clews to deadend properly (see survey notes) |  | W | QUAL | D
replace backstay with 1/4'' wire | someday | W | QUAL
Add block for snubber at end of bowsprit | talking to harken about the right block size for this -- need to put eye pad in as well. It's not clear whether it best to leave the block attached when not in use, however. | W | QUAL
Look into new Yamaha outboard | 9.9HP at Jacobsen's Marine | W | QUAL | D
talk to Boat US about a rider for the coast | US coast will only coast a bit more | W | QUAL | D
Pick up a new Bruce anchor for the main | want part number 'bruba30' for 44# Bruce ($263 at pyacht.com) -- we should keep the CQR for awhile it seems to work OK | W | NICE
find a better storage for Fortress anchor | there's a mounting for this in the drawer on the stbd side next to the companion way ladder | W | QUAL
consider installing 'down' switch for windlass | we have an extra switch, just needs to be installed | W | NICE
Find place to permanently mount main compass | current system requires bracket for compass in companion way hatch board | S | QUAL | D
Clean heat exchanger and replace gaskets | have gaskets from Stewarts
Buy a spare alternator | consider and electrodyne | W | NICE
Install reading lights in the main cabin | parts on order | S | QUAL | D
Flush heat exchanger for the Perkins | Greenwood radiator (should cost around $65 -- a new HE is around $300) | W | NICE | D
Replace prop with MaxProp | someday maybe | E | QUAL
Wax hull | haulout | SW | QUAL | D
install speed transducer | this can be done when the maxprop is being installed -- can theoretically be done while boat is in the water | W | QUAL
Get an impeller puller | Seadog makes one I think | W | QUAL | D
mount a light in engine room |  | W | QUAL | D
Get an alternator tensioner | rig one with a turnbuckle | W | QUAL | D
Get a rig tension gauge | these come in different sizes -- here are our standing rig wire sizes: 9/32” shrouds and stays, 3/8” bobstay, and 7/32” boomkin and bowsprit shrouds. West Marine has these in stock ($150 for the larger one and $79 for the smaller one). Note: we're planning to replace the backstay with a smaller gauge of (1/4'') per Brion's notes. update: ordered these two gauges from sailnet.com and saved $100. | S | QUAL | D
extra screws and grease for maxprop | get these from Roland -- also need another zince | S | QUAL | D
Wax topsides |  | SW | QUAL | D
Get stowaway bag for Fortress anchor |  | S | QUAL
Rewire stereo | also get new speakers | W | QUAL
replace hose clamp rings on stern tube |  | W | NICE
Finish conversion of running lights to LED | have all the parts, have done the stern light already | W | MUST | D | job
Galvanize all chain anchor rodes | need to sort out the transport issues with this one | SW | QUAL
Add two more dorade vents aft | this could wait 'til so-cal but will be necessary in the tropics | SW | NICE
install shunt switch for solar panels | need to do this before the tropics -- may not need one if total amps for charging are less than 4.5 | W | QUAL | D
buy two snatch blocks | these are REALLY expensive -- but we need to heavy duty ones to use with the para-anchor. We could also use one on the bowsprit for the anchor snubber | S | QUAL
get a towable water generator | Get this at ABS Alaskan ($788) -- great article here: http://www.sailnet.com/collections/articles/index.cfm?articleid=jeffre0020 |  | QUAL | D
buy extra boat soap |  | S | QUAL | D
spare parts for outboard (fuel filter and 2 stroke oil) | ballard inflatable | S | QUAL | D
rebed any suspicious deck fittings | the bolt thru the turtle hatch on the stbd side leaks | S | QUAL | D
change engine impeller | and get a new one from Stewart's marine -- we currently have two spares | W | QUAL | D
change engine coolant | also bring extra coolant | W | QUAL
tune autopilot | look this up in the manual | SW | QUAL
make a wind scoop | there are plans for this in one of the L&L books | S | QUAL
investigate cost of health insurance | SALTS | S | QUAL | D
Going away party planning and invites | where should this be held? Cost? | SW | QUAL | D
find and test sea anchor | ??? | SW | QUAL
purchase Baja filter for fuel | fisheries supply | S | QUAL
clean all sunbrella canvas | find canvas shop near the marina | S | QUAL
new mattress | ??? | S | QUAL | D
anchor chain brush | this is really important since we don't plan to have a wash down system | S | QUAL
Buy and fit a riding sail | ??? | S | NICE
reeve halyards internally in the mast -- will require cutting hole in mast | NICE items from TOSS rigging survey | W | NICE
add a spinnaker crane to top of mast for drifter |  | W | NICE
replace running backstays with high moduluous rope |  | W | NICE
Consider SST forestays'il |  | W | NICE
calibrate wind instruments | look this up in the manual | S | NICE
experiment with stereo interfaces to Ipod | if nothing else could buy a cheaper deck w/tape player -- note: there appears to be an 'aux IN' on the back of the stereo. If this is the case we just need to get an RCA to Ipod cable. | S | NICE
mount switch for audio (for inside/outside/all listening) |  | W | NICE | D
Varnish everything else… | companion way hatch frames, interior items etc -- IN PROGRESS 6/17 (Steph) | S | NICE
Get _MEX WX_ book | amazon.com | S | NICE | D
consider fuel gauge options | could got with a pnumatic 'tank tender' system for $1000 to use with water tanks as well | W | NICE | D
get a telephone calling card | ??? | S | NICE
consider a new, more powerful dingy motor | can we do 9.9HP? | W | NICE | D
ratlines under bowsprit | need some plans first | W | NICE
epoxy dry rot in forward hatch |  | S | NICE
figure out how to engineer forward hatch for full range of opening | Replacing the existing hatch with one that has a lower profile may also work | SW | NICE
Replace interior lights with Alpenglow models | ordered these on 2/24 | W | NICE | D
Get a quote from North Sails for a new suit of sails | quote out on 3.9.2004 to Seattle loft | W | NICE | D
Take all sails to loft for inspection | call Quantum for time to come in | S | MUST | D | supply | 2004-07-19
finalize Hansen Bros. storage | move stored items at Zunkers' to perm. storage; go through perm. storage to eliminate some items. 8/23, 10:00 am | SW | MUST | D | job | 2004-08-23
install toilet paper holder | have the parts | S | MUST | D | job
apply rubber cement to base of all ceramic dishes |  | S | MUST | D | job
install another cigarette plug | allows us to use two plugs at once | W | MUST | D | supply
Finish instrument console hatch
Mount bulkhead compass |  | SW | MUST | D | job
Add sew-on hanks to all head sails |  | S | MUST | D | job
Organize pilot berth |  | SW | MUST |  | job
Finish dinghy step |  | SW | QUAL |  | job
Mount block for snubber | eyebolt is mounted, need new 9/16'' block (cheap one from Ronstan) | W | MUST |  | supply
Mount eyebolts and galley strap | need a longer eye bolt | SW | MUST |  | job
Replace critical gaskets in portlights | start with the one above the fo'c's'le | SW | MUST |  | job
mount new tri-color LED/anchor light on mast |  | SW | MUST | D | job
grease bow rollers |  | W | MUST | D | job
add banana plug to aqua gen |  | W | MUST |  | job
add fairleads for new stoppers |  | SW | MUST |  | job
add new stoppers for staysail and main |  | W | MUST | D | job
test new stays'il | while still in PT bay | SW | MUST |  | job
organize paper charts for trip south |  | S | MUST |  | job
replace gasket and flange on coolant header tank | new parts from Stewart's | W | MUST | D | job
replace heat exchanger gaskets and clean | found zinc pencil in raw water side | SW | MUST | D | job
provision for trip south |  | S | MUST |  | supply
meal prep for first few days of trip south |  | S | MUST |  | job
give Wojo a shearing | while on shore power | S | MUST |  | job